## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | web scrapping
PROJECT MANAGER | JAYANTH G S |  | EXECUTION PHASE START DATE:
PROJECT DELIVERABLE | web scrapping web portal |  | EXECUTION PHASE END DATE:
PROJECT SCOPE | Scrap College Details
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
OVERALL PROGRESS | in Progress
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
Initiation : | Project setup | 1 | 2020-06-16 | 2020-06-16 | 1 | COMPLETED
| Create RAID log | 1 | 2020-06-16 | 2020-06-16 | 1 | COMPLETED
| Requiremnt gathering | 1 | 2020-06-16 | 2020-06-16 | 1 | COMPLETED
| Project Charter | 1 | 2020-06-16 | 2020-06-16 | 1 | COMPLETED
| Feasibility Study | 1 | 2020-06-16 | 2020-06-16 | 1 | COMPLETED
PLANNING : | Define project deliverables | 1 | 2020-06-17 | 2020-06-17 | 1 | COMPLETED
| Identify the blockers | 1 | 2020-06-17 | 2020-06-17 | 1 | COMPLETED
| Project plan | 2 | 2020-06-17 | 2020-06-17 | 1 | COMPLETED
| Gate Review | 1 | 2020-06-17 | 2020-06-17 | 1 | COMPLETED
EXECUTION : | DESIGN PHASE
| Identify design requirements | 1 | 2020-06-18 | 2020-06-18 | 1 | COMPLETED
| SRS document | 2 | 2020-06-18 | 2020-06-18 | 1 | COMPLETED
| Gate Review | 1 | 2020-06-18 | 2020-06-18 | 1 | COMPLETED
BUILD PHASE
| Development log | 2 | 2020-06-18 | 2020-06-18 | 1 | COMPLETED
| Develop Team | 2 | 2020-06-18 | 2020-06-18 | 1 | COMPLETED
| Execute project management plans | 3 | 2020-06-18 | 2020-06-19 | 2 | COMPLETED
| Task assignments are executed | 2 | 2020-06-19 | 2020-06-19 | 1 | COMPLETED
| Update project schedule | 1 | 2020-06-23 | 2020-06-23 | 1 | COMPLETED
| Gate Review | 1 | 2020-06-23 | 2020-06-23 | 1 | COMPLETED
TEST PHASE
| Create test plan | 1 | 2020-06-27 | 2020-06-27 | 1 | COMPLETED
| Create test cases | 1 | 2020-06-27 | 2020-06-27 | 1 | COMPLETED
| create traceability matrix | 2 | 2020-06-27 | 2020-06-27 | 1 | COMPLETED
| Gate Review | 1 | 2020-06-27 | 2020-06-27 | 1 | COMPLETED
MONITOR & CONTROL : | Quality deliverables | 2 | 2020-07-09 | 2020-07-09 | 1 | COMPLETED
| Effort & cost tracking | 2 | 2020-07-09 | 2020-07-09 | 1 | COMPLETED
| Performance evaluation | 2 | 2020-07-09 | 2020-07-09 | 1 | COMPLETED
| Status meetings | 1.5 | 2020-07-09 | 2020-07-09 | 1 | COMPLETED
| Update RAID log | 2 | 2020-07-17 | 2020-07-17 | 1 | COMPLETED
| Gate Review | 1 | 2020-07-17 | 2020-07-17 | 1 | COMPLETED
CLOSURE : | Create lessons learned log | 1 | 2020-07-22 | 2020-07-22 | 1 | COMPLETED
| Create a system guide | 0.5 | 2020-07-22 | 2020-07-22 | 1 | COMPLETED
| Project handover | 0.5 | 2020-07-22 | 2020-06-22 | 1 | COMPLETED
PRODUCTION : | Go live | 0 |  |  |  | IN PROGRESS
| Cutover activities | 0 |  |  |  | IN PROGRESS
| Gate Review | 0 |  |  |  | IN PROGRESS